## Sheet1
ID | Story | Estimated Hours | Priority (1-5) | (Expected) Sprint When Finished | Finished
1 | Locally ran chess bot | 2 | 1 | 1 |  | Completed
2 | Create Chessboard on index view | 2 | 1 | 1 |  | In Progress
3 | Create upload bot functionality | 5 | 1 | 1 |  | Incomplete
4 | Create Navbar | 1 | 2 | 1
5 | Delete User uploaded bots | 4 | 1 | 1
6 | Move History for chess games | 5 | 1 | 2
7 | Migrate to Postgressql backend | 8 | 1 | 2
8 | Bot vs Bot implementation | 8 | 1 | 2
9 | Chess Bot Difficulty Selector | 7 | 3 | 2
10 | User Login Functionality | 6 | 1 | 2
11 | Admin User Management (CRUD) | 5 | 1 | 2
12 | User Bot Repository | 12 | 2 | 2
13 | User edit, and delete profile | 3 | 4 | 2
14 | Leaderboard for bots | 4 | 5 | 3
15 | Real Time chess visualizations | 6 | 2 | 3
16 | Tournament Mode | 6 | 5 | 3
17 | Move analysis | 15 | 3 | 3
18 | Download other users public bots | 15 | 3 | 3
z